## KISUMU
KISUMU EOC PROJECT( 1/10/2021 to 31st March 2021)
Phase 1: WEEK 1 (Comencing 4th to 8th Oct.)
|  | Task | Current status | Next step | Action by | Timeline | Expected outcome
Objectives |  | Project Scope: Deployment of SayVU in Kisumu County - EOC | Deployment of SayVU in Kisumu County - EOC; • Administration and Management of incoming Emergency Calls and workflows • Integrate with core and other existing systems • Train and Support users • Autonomous Dispatch and Management of County First Responders | Implementation | KSL & CGK | 1/10/2021 - 31/3/2022
1 |  | Preliminary Meetings with Client | Done | Present MOU & NDA | Dev, Mondoh & Ben | 2021-10-01
2 |  | Present Project MOU & NDA | Project MOU & NDA prepared | Share with Kisumu County Health & Sanitation Chief Officer for Review and Signing - Shared | Dev, Mondoh & Ben | 2021-10-01 | Signature
3 |  | Amendment of MOU & NDA | MOU revised and returned | MOU most likely to be signed on Tuesday 12/10/2021 | Mondoh | 5/10/2021 | Signature
4 |  | Present amended MOU & NDA to the Client
5 | a | Prepare a template sheet for data Collection | Template sheet shared | Brainstorming ongoing match with the research done earlier | Benson | 2021-10-08
| b | Locate all Medical Facilities Identify, Name and Register the Medical facilities in all the Sub-Counties. Naming and registration of the facilities to include the Telephone Numbers, Critical Staff and personnel in Charge | Facility identified and set up done | verification of facilities by subcounty ongoing | D.Wanyande & Benson | 2021-10-08
6 | a | Team leader to identify the Command Centre Office | Space alocated | Need to have a vacuum cleaner Ask Wanyande if someone can take care of the place | D.Wanyande & Benson | 2021-08-10
| b | All Project Materials to be prepared and aligned as per the requirements and scope of the project. | 1 HP Monitor,KEYBOARD & MOUSE, 1 HP Pro Desk, 2 HDMI- VGA converter, Kasperky antivirus, Microsoft office 2019, Windows 10 pro licensing, 1 LB-link USB Wifi adaptor, 2 Bluetooth Headsets, 1 Hisense Smart TV, 5 Samsung Galaxy A7 Tablets, 5 Tab leather covers, 2 Foldable seats, 2 Tables, 1 Chair
7 | a | Technical-operate the Command & Control Centre | The IT has a team of 3 people under Kennedy. We need atleast 6 people fro our side | Get interns to be part of the team Help the team understand the EOC process and manage it as we oberve all through | Mondoh, Benson & Beatrice | 1/10/2021 to 12/10/2021
| b | Field Teams-To Market and popularize the EOC | Need to get the full list from David to determine further action | Recruit our field team to market and give support | Mondoh | 2021-12-10
| c | Administration -To coordinate and offer logistical support
8 |  | Procure Telephone Lines from Safaricom & Airtel Secure, register and load Data on phone lines to be used in the Mobile Units to be installed in the Ambulances | Procured | Installation and Data loading to be done today 6/10/2021 | Benson | 2021-10-06
9 |  | Mapping of the medical facilities and relevant Points of Interest & generate GPS Coordinates for each facility | Medical facilities and point of interest mapped GPS coordinates generated |  | Benson & Wanyande | 2021-05-10
10 |  | EOC Command and Control Setup | Installation of the software & configuration of the hardware done on 5/10/2021 | installation of the software and configuration of the hardware on the tablets to be done today on 6/10/2021 | Benson | 2021-06-10
11 |  | Mobile CC Setup | David to help - Not yet. suggestion to have the dashboard at subcounties Kevin concerned on skill set of drivers | Install the Hardware and configure the Software in the Ambulances (5 for a Start) all ambulances to be notified from the EOC | Benson | 2021-10-11
12 | a | Creating an Exclusive SayVu Platform domiciled only for Kisumu County | This is on course being carried out by Amotz and team | Amotz & team to be around Excel sheet shared Amotz to set up the hardware and open the C&C Center | Benson/Amotz/Mondoh | 8/10/2021 to 12/10/2021
| b | Categorization of the Modules and Contracts | Creating of Multiple Categories of Contracts Unique to Kisumu County
Week 2 Commencing on 11th to 15th Oct.2021
13 | a | EOC Instance User Matrix | Excel sheet Shared Benson working on it | Creating of the Command & Control Dashboard Users and assigning of Roles and Privileges Benson to use the list and create an organogram | Benson/David | 8/10/2021 to 12/10/2021
| b | Test and Verify the User Matrix works as expected
| c | Map Users to respective Categories and Contracts
| d | Test and Verify the EOC C&C Instance with domiciled Categories Test the Mobile C&C Stations
14 |  | Train Users and Stakeholders at various levels | Pending |  | Benson & Wanyande | 13/10/2021 to 18/10/2021
15 |  | Hand Over and Go Live | Pending |  | Benson & Wanyande | 2021-10-18
16 |  | Launch the EOC | Pending |  | KSL & CGK | 20/10/2021
17 |  | Monitoring and evaluating the project per phase
18 |  | Prepare detailed project evaluation report
Key:
|  | 1 |  | Task is done
|  | 2 |  | Task is overdue/New task that needs action
|  | 3 |  | Task is ongoing or underway
|  | 4 |  | Task is normal

## ADMIN
KENLINKS SOLUTIONS LTD
P.O. Box 102576-00101
Nairobi, Kenya.
Phone: +254701922922
Website: www.kenlinksolutions.com
Pin: P051806893B
Department:
| Task | Current status | Next Step | Responsibility | Deadline | Expected Outcome
1 | Staff Work plans | Done | Sharing for more input | Beatrice | 23/7/2021 | workflow management and timely follow up
2 | Project Work plan | Done | Share for input | Beatrice & Dave | 26/7/2021 | Easy follow up
3 | Social Media | Twitter, Instagram and facebook accounts have been created. So far; 1. Facebook - Kenlinks Solutions - SayVu Africa from 19/7 we have 8 posts in the last 28 days page visit is at - 207 page reach is at - 369 page likes is at - 329 post engagement is at - 45 Our page audience is mostly fron nairobi,most of them are men. 2. Instagram - Kenlinks Solutions we have 2 posts so far We have 23 to 24 followers 3. Twitter - Kenlinks solutions Ltd- SayVu We have 3 to 4 followers | We need to; 1. Give incentives/packages to our new subscribers 2. Upadate them with new relevant information like titbits 3. Encourage them to share about our app to their groups 4. Becoming consistent | All | continous | Market our app and get more subscribers
4 | Nairobi county Hospitals | Done | Done | Benjamin &Ritar | 30/7/2021 | Partnering up
5 | Nairobi county police stations research | Done | Mapping the police stations.- This is also done | Benjamin &Ritar | 19/07/2021 | Create a partnership
6 | Emails | Benson to give guidance and have the following emails working 1. support@kenlinksolutions.com 2. info@kenlinksolutions.com 3. solutions@kenlinksolutions.com Benjamin to create a tool which can show if emails have been delivered, opened and read | Done | Benson & Benjamin |  | Easy communication
7 | Subsciption: CODE | Having challenges with the delaying code | Benson to talk with Roman and see what to be done | Benson & Benjamin |  | Speedy and easy subscription process
8 | Social Media content | plan to have enough suitable and relevant content to post on our social media accounts | Done | Beatrice | Continuous | Update, engage and gain more subscribers
9 | Product Knowledge | We need to know what we are selling | Read widely Go through the presentations and learn | All | Continuous | Able to market and win clients
10 | Subscribers | Have an automated message to remind,thank, inform and help them stay in touch | SMS availabe | Beatrice/Benson/Roman | Continuous | Staying in touch with subscribers
11 | Website | Good presentation for the start however we need to make it catchy | Need to put pictures that communicate Pull the reader to want more Choose our wordings to captivate the reader Not to create an impression of panic but bring hope | Benja/Benson |  | Communicate with clients
12 | Mpesa dedicated office line | The line is there | Need to be put in use | Kizito/Mondoh |  | Easy acounts follow up
13 | Electricity | Follow on the hyked bill |  | Benson |  | Payment ongoing
14 | Client letters | Edit, print on letter head and Address them | 1. KISIA 2. National police Service 3. Kenya Police Service 4. Administration police Service 5. Director Criminal investigation 6. Ministry of interior 7. Regional Police Commander | Beatrice/Ritar | 5/8/ | done
15 | Request for office items | Send the requisition for approval | Sent not approved yet | Beatrice | 2021-04-08 | Some items bought
16 | Liquid | Most of the work is done | Final stage to be done today or tomorror( 9/8 -10/8) | Beatrice/Benson | 2021-10-08 | Done
17 | July Reports | All written | Sent to Mr. Mondoh |  | 2021-03-08 | Done
18 | New Subscribers | Steve - Language setting Ignitious - tried the app Armstrong - Smooth sub. process will try the app when free Benedict - subscribed and tried the app | Steve was helped and tried the app Ignitious was helped and tried the app | Beatrice/Benja/Ritar | Closed
19 | Presentation - SayVu | Reconstruct the Enterprise Architecture Diagram Script Who,What and How | Update it and make it relate with what we offer | Benja/Beatrice/Ritar | done
20 | SayVU Competitors Research | Aura/Secura Namola | Check what to borrow How they do it |  | done
21 | Rising issues | Record in a book and state action taken | Give feedback untill the issue is closed | Beatrice/Benja | book available with logs updates
22 | Website | presentation of the website progress |  | Benjamin
23 | Generator | check it once a week | fuel,battery and run it for 30mins and keep logs | Beatrice/Benja | 30/08/2021 checked | continous